Handout:  Examples of forms for planning a cost study

| Project Timeline (DRAFT- to be finalized with input from Project coordinator) |
| --- |
| Activities |  |  |  |  | MONTH |  |  |  |  |  |
|  | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT |  |
| Develop generic data collection forms |  |  | XXX | XXX |  |  |  |  |  |  |
| Field Activities |  |  |  |  |  |  |  |  |  |  |
| Review current programs |  |  |  |  | XX | XX |  |  |  |  |
| Describe three intervention strategies |  |  |  |  | XX | XX |  |  |  |  |
| Visit sites: education, health, and community facilities, interview education, health, and community workers |  |  |  |  |  | XX | XX |  |  |  |
| Gather facility information from schools, health centers and community organizations |  |  |  |  |  | XX | XX |  |  |  |
| Develop questionnaires for parents and caretakers |  |  |  |  |  |  | XX |  |  |  |
| Revise draft survey form(s) using new information |  |  |  |  |  |  | XX |  |  |  |
| Review and revise the draft form with team |  |  |  |  |  |  | XX |  |  |  |
| Select the sample of facilities and delivery sites. |  |  |  |  |  |  | XX |  |  |  |
| Pretest the survey |  |  |  |  |  |  | XX |  |  |  |
| Revise the survey form |  |  |  |  |  |  |  | XX |  |  |
| Translate the form(s) |  |  |  |  |  |  |  | XX |  |  |
| Develop instruction manual if necessary |  |  |  |  |  |  |  | XX |  |  |
| Visit sites and collect data using revised data forms |  |  |  |  |  |  |  | XX |  |  |
| Data entry and cleaning |  |  |  |  |  |  |  |  | XX |  |
| Data analysis |  |  |  |  |  |  |  |  | XX |  |
| Report writing |  |  |  |  |  |  |  |  | XX |  |

Appendix A

LIST OF COST STUDY DATA REQUIREMENTS

DATA TYPE				LEVEL		COLLECTION METHOD

- Start-up costs

-Program development				records

--Government meetings				records

-Personnel

-Facilities

- Training costs

- Personnel				records

- Facilities				records

- Materials				records

- Per diems (snacks,etc.)				records

- Logistic support				records

- Advocacy and Promotion (for recruitment and project implementation)

-Public meetings				records

-Behavior change/comm.				records

Materials

- Personnel

- Brochure/Poster development

- Printing

4. Contact costs (costs to reach target, recruitment, and carry out intervention)

-  Salary/time of health personnel		records/observation

-  Salary/time of education personnel 	records/observation

-  Salary/time of community personnel	records/observation

- Salary/time of lay personnel			records/observation

- Materials development, mass media	records

And  Supplies

6. Transportation

- Personnel transport			facility/individual 	questionnaire

- Unit fuel price			facility	questionnaire

- Monitoring and Evaluation

-Office supplies			records

- Paper			records

- Photocopying  			records

- Administrative personnel		records

- (Supervisory personnel included in 4 above)

Appendix B

STEPS IN DESIGNING AND PRE-TESTING COST STUDY SURVEY FORMS

- Describe strategic interventions to reach girls aged 10-14 years old to promote health and responsible sexuality through educational activities and strengthening of community support networks that increase knowledge, improve attitudes and develop skills.

- Prepare worksheets for collecting information on start-up costs, training costs, and workshop costs that can be used early on in the project implementation phase.

- Prepare guidelines for expense report to ensure cost breakdowns are available from implementing partners –CEPS and Puntos de Encuento

- Collect background data and information from Ministry of Health and Government Statistics Office .

- Demographic and socio-economic data.

- Current salary rates, benefits, basic consulting rates and other allowances for Ministry of Health for personnel working in public health clinics (providing reproductive health services to women).

- Ministry (Health, Education, Community Development) transport allowances, transport, per diems, etc. for civil servants.

- Information on education curriculum and health service delivery system (public, private, NGO) .

- Identify possible health economists to contact and exchange information with.

- Activities toward understanding the components of the intervention as input into collecting cost data that is complementary to expense reports.

- Visit sites where peer education support is taking place and interview participants on their involvement in the intervention.

- Visit schools, health facilities, and community organizations involved in the support network support activities and interview staff who are involved in the intervention.

- Visit parents and caretakers and interview them on their involvement in the intervention.

- Visit organizations participating in mass media programs and material development.

6.  During visits to schools, health facilities, community organizations, etc., make a list of the following types of information (where possible, indicate which resources are shared with other programs):

- All of the activities of the intervention: recruitment, training, meetings, supervision, and management.

- Identify and describe the resources used to select promoters (group leaders) and to form a group of adolescent girls.

- Understand components of recruitment.

- Understand components of the training program.

- Identify training and educational materials used and what types of activities are used.

- Describe the types of personnel involved for all activities .

- List the type of supplies and materials used for regular meetings.

- List use of space and vehicles used for the intervention activities (for personnel and supplies).

- Describe monthly patterns of supervision and by whom.

- Desribe strategies for motivating the population and who does this activity.

- Discuss with program managers the operations of current programs, including the strengths and weaknesses at different levels of the community, health and educational systems that are working with the project.

- Using information collected, revise the draft survey form(s) to closely match the way data are recorded in health clinic registers.

- Review the draft forms with the study team, the project managers, and others.

- Revise the draft form based on initial comments and feedback from reviewers.

- Select the sample of facilities.

- Pretest the survey form in a facility or delivery site not included in the sample.

- Revise the survey form based on the pre-test.

- Translate the forms (this may happen much earlier in the process).

- Develop instructions and a list of probe questions for eliciting survey responses.